## START HERE
Customer onboarding dependency map | LaunchHandoff · operating workbook
Purpose | A daily blocker list with one owner and one useful next action
Use it for | B2B SaaS teams with 5–20 implementation or customer-success managers
1 | Read the worked example before changing any headings.
2 | Copy the EXAMPLE DATA structure into CUSTOMER ONBOARDING DEPENDENCY REGISTER and replace every fictional token.
3 | Use tokens instead of names. Keep credentials, documents, message content, and sensitive data out of this workbook.
4 | Complete the WEEKLY REVIEW with the people who own the decisions. Evidence can inform a decision; it cannot make one.
5 | Agree every metric definition before comparing periods, teams, suppliers, or customers.
Workbook tabs | START HERE · WORKING REGISTER · EXAMPLE DATA · WEEKLY REVIEW · METRIC DICTIONARY
Safety boundary | No autonomous commitments to customers, unrestricted inbox access, forced portal migration, or claim that reminders alone change behavior.
Template status | The example rows are fictional. Adapt the workbook to your policy and source systems before operational use.
Check 1 | Separate customer-owned, internal, and third-party tasks
Check 2 | Give every blocker one owner and unblock condition
Check 3 | State the downstream impact in every follow-up
Check 4 | Escalate based on impact and elapsed time—not reminder count

## WORKING REGISTER
Project token | Task token | Safe task label | Owner party | Owner role token | Status | Created UTC | Due UTC | Promised UTC | Last status change UTC | Last contact UTC | Blocker code | Impact class | Downstream milestone token | Predecessor task token | Successor task token | Dependency type | Required | Next action code | Action owner | Review date

## EXAMPLE DATA
Project token | Task token | Safe task label | Owner party | Owner role token | Status | Created UTC | Due UTC | Promised UTC | Last status change UTC | Last contact UTC | Blocker code | Impact class | Downstream milestone token | Predecessor task token | Successor task token | Dependency type | Required | Next action code | Action owner | Review date
PRJ-001 | TSK-008 | Configuration input | Customer | ROLE-C02 | Blocked | 2026-08-22 09:00 | 2026-08-29 17:00 | 2026-09-01 12:00 | 2026-08-28 10:10 | 2026-08-28 10:15 | INPUT-MISSING | High | MILE-003 | TSK-006 | TSK-011 | Finish-to-start | Yes | REQUEST-CONFIRMATION | ROLE-I01 | 2026-09-01
PRJ-002 | TSK-012 | Technical review | Internal | ROLE-I03 | In progress | 2026-08-25 11:00 | 2026-09-03 17:00 |  | 2026-08-31 15:20 |  | NONE | Medium | MILE-002 | TSK-010 | TSK-015 | Finish-to-start | Yes | COMPLETE-REVIEW | ROLE-I03 | 2026-09-01
PRJ-003 | TSK-004 | Access confirmation | Third party | ROLE-T01 | Waiting | 2026-08-26 08:30 | 2026-09-02 12:00 | 2026-09-02 12:00 | 2026-08-30 09:00 | 2026-08-30 09:05 | EXTERNAL-WAIT | High | MILE-001 | TSK-002 | TSK-007 | Finish-to-start | Yes | CONFIRM-OWNER | ROLE-I02 | 2026-09-01

## WEEKLY REVIEW
Review question | How to inspect it | Decision to record | Owner | Decision | Next review date
Which customer-owned tasks block a milestone? | Filter Owner party = Customer and inspect downstream milestone and dependency fields. | Prioritize business impact, not reminder count.
Does every blocker have an unblock condition? | Review Blocker code, Next action code, and Action owner. | Replace vague chasing with a concrete request.
Which promised dates have slipped? | Compare Promised UTC with status and the review date. | Ask the buyer to confirm a new date.
Are dependency edges explicit enough? | Find required tasks without predecessor, successor, or milestone links. | Repair the plan before judging delay.
Did follow-up move the task? | Compare Last contact UTC with Last status change UTC. | Record movement without claiming causation.

## METRIC DICTIONARY
Metric | Definition | Required fields | Cadence | Owner | Target | Notes
Customer-blocker age | Days since Last status change for open customer-owned blockers | Owner party; Status; Last status change UTC | Daily
Dependency coverage | Required tasks with an explicit dependency or downstream milestone | Required; Predecessor; Successor; Downstream milestone | Weekly
Promised-date reliability | Tasks completed by the buyer-confirmed promised date divided by tasks promised | Promised UTC; Status; Last status change UTC | Weekly
Blocked milestone exposure | Distinct downstream milestones affected by open blockers | Status; Downstream milestone token | Daily
Movement after review | Prioritized tasks changing state by the next snapshot divided by prioritized tasks | Review date; Last status change UTC | Per review cycle